## ورقة1
Type | Current Situation / Considerations | Proposed Solution / Benefits | Feasibility Result
Technical | Manual management of matches, team data, and spreadsheets causes schedule conflicts and errors. | Web-based system with database (MySQL/PostgreSQL) and automated fixture generation algorithms. | ✅ Technically feasible
Operational | Manual tournament coordination is time-consuming, prone to overlapping stadium bookings, and hard to track. | Automated round-robin/knockout generation; easy tracking; reduced scheduling workload; zero conflicts. | ✅ Operationally feasible
Economic | Cost of software development, server hosting, maintenance, and manual planning overhead. | Saves time and money; reduces administrative errors; long-term efficiency gains and reduced coordination costs. | ✅ Cost-effective
Legal | Need compliance with sports data privacy, fair play regulations, and terms of use. | Implement data privacy/security policies; ensure compliance with regulations and tournament fair-play rules. | ✅ Legally feasible
Schedule | Manual scheduling processes delay tournament planning and league kickoff dates. | Estimated timeline 3-6 months (requirements ➔ design ➔ development ➔ testing). | ✅ Achievable timeline

## ورقة2
Perfect 👍 Here’s a Cost–Benefit Analysis Table for the Library Management System (LMS):
Cost-Benefit Analysis - League Fixture Generator System
Category | Description | Estimated Cost | Benefits | Estimated Value (per year)
Software | Development (in-house) or purchase of League Fixture Generator software license | $2,000 – $3,000 | Centralized, automated system reduces scheduling and fixture errors | $2,500 savings in admin errors & schedule conflicts
Hardware | Server, hosting infrastructure, and backup drives for the web application | $1,000 – $1,500 | Faster schedule generation; reduced manual coordination time | $2,000 saved in manual coordination workload
Training | Staff and tournament organizers training sessions | $300-$500 | Smooth transition, efficient management of teams, venues, and matches | Higher productivity (= $1,000)
Maintenance | Annual software updates, bug fixes, and server hosting support | $700 – $1,000 | Ensures system reliability, secure match database, and conflict prevention | $1,500 saved from system downtime and manual delays
Administration | Current manual system (spreadsheets, paper forms, manual scheduling) | $800-$1,200 | Eliminated manual sheets -> automated digital system | $1,000 saved from paperless process
User Experience | Manual fixture generation wastes time and causes scheduling conflicts for teams and organizers | – | Faster access to match results, standings, and improved user satisfaction | Intangible but high value (better tournament management experience)
## Summary
Total Estimated Costs (first year): $4,000 – $5,000
Total Estimated Annual Benefits/Savings: $5,000 – $7,000
Payback Period: Within 1 year
Conclusion:The League Fixture Generator System is economically feasible, with clear cost savings and long-term value.